## Overview
PROJECT SUMMARY
A clear plan for opening day.
Tie each opening issue to a person, a date and a check that proves it is done.
EXAMPLE ONLY ¦ Five sample actions are included. Replace these details before using this for a real opening.
Project / location |  | [Enter project or store name]
Opening lead |  | [Enter lead name]
Opening date
Review date
Blue cells are editable. Date fields are blank until you enter your project dates.
OPEN ACTIONS | COMPLETE |  | BLOCKED |  | OVERDUE | NO OWNER
5 | 0 |  | 0 |  | 0 | 5
Three steps to use this tracker
1. Enter the project, opening lead and dates above. The sample due dates will fill in for you.
2. Open Action tracker. Name an owner, check the due date and choose a status. Add the test result and latest update.
3. Read Action details for the full steps. Mark Complete only when the agreed check has passed and the result is recorded.
Open Action tracker → |  |  |  | Open Action details →
What each status means
Not started |  | An owner and next step still need to be agreed.
In progress |  | The owner is working on the action.
Blocked |  | A task or decision is blocked. Call the person who can help.
Ready to verify |  | The work is done. The final check still needs a review.
Complete |  | The agreed check has passed. The result is recorded.
Due dates are starting points. Confirm them with your vendors. Adjust them to fit your plan. Amber owner or date cells need a check. Red dates are late. This tracker does not approve a store to open.
Formulas:
OVERDUE = COUNTIFS(OpeningActions[Action],"<>",OpeningActions[Due date],">0",OpeningActions[Due date],"<"&TODAY(),OpeningActions[Status],"<>Complete")

## Action tracker
OWNERS · DATES · EVIDENCE
Opening action tracker
Five sample issues. Keep this view short. Read Action details for the full steps and checks.
Blue cells can be edited. Choose a status from the list. Confirm due dates with the owner. Add new actions below the table.
Priority | Action | Named owner | Due date | Status | Evidence link | Latest update | Action ID
1 | Prove checkout works when the internet goes down. |  |  | Not started |  |  | KDA-01
2 | Check that payments use this store’s account and reach the bank. |  |  | Not started |  |  | KDA-02
3 | Test orders and printers at a busy pace. |  |  | Not started |  |  | KDA-03
4 | Give each shared vendor task one owner and a due date. |  |  | Not started |  |  | KDA-04
5 | Agree who can pause the launch and who answers a support call. |  |  | Not started |  |  | KDA-05
Note on B9: Supporting instructions and completion criteria are on the Action details tab.
Note on D9: Example timing: 14 days before opening. Override this date if the agreed plan differs. Priority 4 calculates two working days after the review date; its handoff milestone is also recorded in Action details.
Note on F9: Link to a shared test result or completion record. Do not put full card or bank details in the tracker.
Note on B10: Supporting instructions and completion criteria are on the Action details tab.
Note on D10: Example timing: 14 days before opening; settlement confirmed within the provider’s expected window. Override this date if the agreed plan differs. Priority 4 calculates two working days after the review date; its handoff milestone is also recorded in Action details.
Note on F10: Link to a shared test result or completion record. Do not put full card or bank details in the tracker.
Note on B11: Supporting instructions and completion criteria are on the Action details tab.
Note on D11: Example timing: 7 days before opening. Override this date if the agreed plan differs. Priority 4 calculates two working days after the review date; its handoff milestone is also recorded in Action details.
Note on F11: Link to a shared test result or completion record. Do not put full card or bank details in the tracker.
Note on B12: Supporting instructions and completion criteria are on the Action details tab.
Note on D12: Example timing: Owners and dependencies within 2 working days; handoffs checked 10 days before opening. Override this date if the agreed plan differs. Priority 4 calculates two working days after the review date; its handoff milestone is also recorded in Action details.
Note on F12: Link to a shared test result or completion record. Do not put full card or bank details in the tracker.
Note on B13: Supporting instructions and completion criteria are on the Action details tab.
Note on D13: Example timing: 7 days before opening; final check 1 day before opening. Override this date if the agreed plan differs. Priority 4 calculates two working days after the review date; its handoff milestone is also recorded in Action details.
Note on F13: Link to a shared test result or completion record. Do not put full card or bank details in the tracker.

## Action details
EXAMPLE ACTION 01 / 05
EXAMPLE ONLY ¦ Replace these steps with your project facts.
Prove checkout works when the internet goes down.
Review finding | Possible risk. Test results are still needed.
Who follows up | Internet, checkout and payments providers. The opening owner brings them together.
Target timing | 14 days before opening.
Next action | Plan an outage test with the providers. Test a sale, an order and a receipt on the agreed backup. If you use payments without internet, follow the approved steps. Then bring the main internet back.
Completion check | Record the test result, time to switch and what happens when the main internet returns. Write down any limits on selling. If offline payments are allowed, get the limits approved by the provider. Check that each payment is sent only once when service returns.
NAMED OWNER |  | DUE DATE | WORKFLOW STATUS
Unassigned |  |  | Not started
Update the owner, due date, status and test results on Action tracker. A missing test result does not prove a system is broken.
EXAMPLE ACTION 02 / 05
EXAMPLE ONLY ¦ Replace these steps with your project facts.
Check that payments use this store’s account and reach the bank.
Review finding | Possible risk. Account and payment records are still needed.
Who follows up | Payments provider and finance, with the checkout vendor.
Target timing | 14 days before opening. Check bank arrival on the provider’s timetable.
Next action | Ask the provider to check the store account on each card machine. Follow its approved steps for a small real payment. Test a refund or void if the provider supports it.
Completion check | Record which store account each card machine uses and the successful payment result. Finance checks that the money reaches the right account on time and resolves any gap. Keep full card and bank details out of the shared tracker.
NAMED OWNER |  | DUE DATE | WORKFLOW STATUS
Unassigned |  |  | Not started
Update the owner, due date, status and test results on Action tracker. A missing test result does not prove a system is broken.
EXAMPLE ACTION 03 / 05
EXAMPLE ONLY ¦ Replace these steps with your project facts.
Test orders and printers at a busy pace.
Review finding | Possible risk. The team has only described one test ticket.
Who follows up | Store manager and checkout or ordering vendor.
Target timing | 7 days before opening.
Next action | Agree how many orders to test and how fast they must arrive. Test every order route to the right kitchen station, screen or printer. Include changed and cancelled orders. Test how to recover a failed order.
Completion check | Match the orders sent with the orders received. Check that none are missing, doubled or sent to the wrong place. Check that each arrives within the agreed time. Record how failed or changed orders were handled. Retest any fix.
NAMED OWNER |  | DUE DATE | WORKFLOW STATUS
Unassigned |  |  | Not started
Update the owner, due date, status and test results on Action tracker. A missing test result does not prove a system is broken.
EXAMPLE ACTION 04 / 05
EXAMPLE ONLY ¦ Replace these steps with your project facts.
Give each shared vendor task one owner and a due date.
Review finding | Gap in the plan. Named owners are missing.
Who follows up | Operations or project manager, with the contractor, installer and tech vendors.
Target timing | Name owners and tasks within 2 working days. Check shared tasks 10 days before opening.
Next action | Name one owner for each shared task. Confirm firm dates for site access, gear, internet, installs, tests and staff training. Write down what each vendor needs from the one before it.
Completion check | Each task has an owner, a due date, a list of what must happen first and proof it is done. Any missed or unconfirmed date has a next step and a contact to call for help. The opening owner keeps the shared list up to date.
NAMED OWNER |  | DUE DATE | WORKFLOW STATUS
Unassigned |  |  | Not started
Update the owner, due date, status and test results on Action tracker. A missing test result does not prove a system is broken.
EXAMPLE ACTION 05 / 05
EXAMPLE ONLY ¦ Replace these steps with your project facts.
Agree who can pause the launch and who answers a support call.
Review finding | Gap in the plan. Launch rules and support hours are missing.
Who follows up | Operations leader, store manager and each support vendor.
Target timing | 7 days before opening. Final check 1 day before opening.
Next action | Name who makes the opening decision. Agree the checks that must pass and when to call for help if a test fails. Get backup steps approved by the providers. Confirm support names and hours for opening weekend.
Completion check | Staff have the decision rules, call list and backup steps. Contacts and support hours are confirmed. Key checks have results. The operations leader writes down the final opening decision.
NAMED OWNER |  | DUE DATE | WORKFLOW STATUS
Unassigned |  |  | Not started
Update the owner, due date, status and test results on Action tracker. A missing test result does not prove a system is broken.

## Lists (hidden)
Not started
In progress
Blocked
Ready to verify
Complete